## Sheet1
Item No | Discription of Item to be loaded | Item ID | Owner of Item | Length (mm) | Width (mm) | Height (mm) | Weight (Kg) | Load location | Projected load Date | Projected off load Date | Where item is to be located | Comments | Hazards | Risk
21 | Reel stand and Spooling gear Grillage | ACE3761 | ACE | 4885 | 3856 | 327 | 4659 | SHI | 2020-07-01 |  | North Side | definite korea install | 1 | 0
22 | Reel stand and Spooling gear Grillage | ACE3761 | ACE | 4885 | 3138 | 327 | 4432 | SHI | 2020-07-01 |  | North Side | definite korea install | 0 | 0
23 | Reel stand and Spooling gear Grillage | ACE3761 | ACE | 729 | 70 | 1200 | 350 | SHI | 2020-07-01 |  | North Side | definite korea install | 0 | 0
30 | West Moon Pool steering winch grillage | ACE3765 | ACE | 14222 | 2506 | 377 | 7861 | SHI | 2020-07-01 |  | Moon Pool - Main Deck | definite korea install | 1 | 0
39 | East Moon Pool steering winch grillage | ACE3766 | ACE | 14222 | 2506 | 377 | 7861 | SHI | 2020-07-01 |  | Moon Pool - Main Deck | definite korea install | 0 | 1
49 | ACE 110kW Diesel Hydraulic Power Unit DHPU - West grillage | ACE 2166BF | ACE | TBC | TBC | TBC | TBC | SHI | 2020-07-01 |  | Moon Pool - Main Deck | definite korea install | 0 | 0
50 | ACE 110kW Diesel Hydraulic Power Unit DHPU - East grillage | ACE 2166BF | ACE | TBC | TBC | TBC | TBC | 3 | 2020-07-01 |  | Moon Pool - Main Deck | definite korea install | 0 | 0
61 | ACE 550Te SWL Linear Winch South East Corner Grillage (1) | ACE3727 | ACE | 8200 | 3500 | 1885 | 7495 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 0 | 0
62 | ACE 550Te SWL Linear Winch South East Corner Grillage (2) | ACE3727 | ACE | 8200 | 3500 | 635 | 7020 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 0 | 0
63 | ACE 550Te SWL Linear Winch South East Corner Grillage (3) | ACE3727 | ACE | 4924 | 2876 | 2206 | 11394 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 0 | 1
64 | ACE 550Te SWL Linear Winch South East Corner Grillage (3) | ACE3727 | ACE | 4924 | 2876 | 2389 | 12643 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 1 | 0
69 | South East Corner reel stand / spooling gear grillage | ACE3762 | ACE | 4653 | 3750 | 876 | 3710 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 0 | 1
79 | East pull in Grillage (1) | ACE3763 | ACE | 8240 | 4260 | 2540 | 16168 | SHI | 2020-07-01 |  | East Side | definite korea install | 0 | 0
80 | East pull in Grillage (2) | ACE3763 | ACE | 12000 | 3500 | 921 | 13327 | SHI | 2020-07-01 |  | East Side | definite korea install | 0 | 0
81 | East pull in Grillage (3) | ACE3763 | ACE | 12000 | 3500 | 921 | 13327 | SHI | 2020-07-01 |  | East Side | definite korea install | 0 | 0
82 | East pull in Grillage (4) | ACE3763 | ACE | 6996 | 3500 | 921 | 11573 | SHI | 2020-07-01 |  | East Side | definite korea install | 0 | 0
83 | South pull in Grillage | ACE3764 | ACE | 14863 | 4217 | 1611 | 20500 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 1 | 0
1 | 550 Te SWL Zone 2 linear winch | ACE3640 | ACE | 8620 | 2885 | 1635 | 46000 | SHI | 2021-02-01 |  | North Side | Likely install in Korea, GoM Contingency | 0 | 0
2 | ACE 220kW Zone 2 Diesel Hydraulic Power Unit | ACE 470 | ACE | 6170 | 2540 | 2790 | 15000 | KOS | 2021-02-01 |  | North Side | No-weld, Bolt-up | 0 | 0
3 | ACE 550Te SWL Linear Winch Hang off | ACE3726 | ACE | 4814 | 1410 | 2959 | 10948 | SHI | 2021-02-01 |  | North Side | Likely install in Korea, GoM Contingency | 0 | 0
4 | ACE 550Te SWL Linear Winch Hang off | ACE3726 | ACE | 3904 | 1010 | 3045 | 5067 | SHI | 2021-02-01 |  | North Side | Likely install in Korea, GoM Contingency | 0 | 0
5 | ACE 550te Trunnion Arrangement | ACE3731 | ACE | TBC | TBC | TBC | 2000 | SHI | 2021-02-01 |  | North Side | Likely install in Korea, GoM Contingency | 0 | 0
New | Control Cabin Steel Beams for Seafastening (x2) | [6 empty] | SHI | 2021-02-01 |  | North Side | definite korea install | 0 | 1
6 | 16' Control Cabin | ACE 3566 | ACE | 4877 | 2438 | 2590 | 6395 | KOS | 2021-02-01 |  | North Side | No-weld, Bolt-up | 1 | 0
7 | Interconnecting Hose Set (special) | UM677 | ACE | 1700 | 1700 | 700 | 340 | KOS | 2021-02-01 |  | North Side |  | 0 | 0
8 | Interconnecting Hose Set (special) | UM680 | ACE | 1700 | 1700 | 700 | 340 | KOS | 2021-02-01 |  | North Side |  | 0 | 1
9 | Interconnecting Cable Set | IC3640 | ACE | 1700 | 1700 | 700 | 340 | KOS | 2021-02-01 |  | North Side |  | 0 | 0
10 | Water Cooling Hoses Set | N/A | ACE | 1230 | 1230 | 439 | 300 | IPL | 2021-02-01 |  | North Side |  | 0 | 0
11 | Air start hose | N/A | ACE | 1230 | 1230 | 439 | 300 | IPL | 2021-02-01 |  | North Side |  | 0 | 0
12 | Wire rope package | WR 1048-01 | ACE | N/A | N/A | N/A | 30000 | SHI | 2021-02-01 |  | North Side | Likely install in Korea, GoM Contingency | 1 | 0
13 | Northside wire rope storeage drum | ACE3757 | ACE | 2750 | 3500 | 3500 | N/A | SHI | 2021-02-01 |  | North Side | Likely install in Korea, GoM Contingency | 0 | 1
14 | ACE 125Te SWL Zone 2 Hydraulic Reel | ACE3760 | ACE | 2200 | 5000 | 3280 | 9500 | SHI | 2021-02-01 |  | North Side | Likely install in Korea, GoM Contingency | 0 | 0
15 | ACE Stand Alone Spooling Gear | ACE1762 | ACE | 4720 | 1380 | 4336 | 5960 | KOS | 2021-02-01 |  | North Side | No-weld, Bolt-up | 0 | 0
16 | ACE 75 Tonne WLL 3 Rollerbox | ACE2083 | ACE | 1800 | 870 | 1105 | 1850 | KOS | 2021-02-01 |  | North Side | No-weld, Bolt-up | 1 | 0
17 | ACE 60kW Open Loop Zone 2 Diesel | ACE1799 | ACE | 2500 | 1330 | 2040 | 3500 | KOS | 2021-02-01 |  | North Side | No-weld, Bolt-up | 0 | 0
18 | Interconnecting Cable Set | UM365 | ACE | 1230 | 1230 | 430 | 300 | KOS | 2021-02-01 |  | North Side |  | 0 | 0
19 | Water Cooling Hoses Set | N/A | ACE | 1230 | 1230 | 430 | 300 | IPL | 2021-02-01 |  | North Side |  | 0 | 0
20 | Air start hose | N/A | ACE | 1230 | 1230 | 430 | 300 | IPL | 2021-02-01 |  | North Side |  | 1 | 0
24 | ACE 144 Tonne WLL Hydraulic drum winch | ACE1693 | ACE | 2904 | 2404 | 2438 | 30000 | KOS | 2021-02-01 |  | Moon Pool - Main Deck | No-weld, Bolt-up | 0 | 0
25 | ACE 144 Tonne WLL Hydraulic drum winch, sliding base frame | ACE1713 | ACE | 4250 | 2708 | 390 | 6000 | KOS | 2021-02-01 |  | Moon Pool - Main Deck | No-weld, Bolt-up | 0 | 0
26 | Interconnecting Cable Set | UM563 | ACE | 1230 | 1230 | 430 | 300 | KOS | 2021-02-01 |  | Moon Pool - Main Deck |  | 0 | 0
27 | Water Cooling Hoses Set | N/A | ACE | 1230 | 1230 | 430 | 300 | IPL | 2021-02-01 |  | Moon Pool |  | 0 | 0
28 | Air start hose | N/A | ACE | 1230 | 1230 | 430 | 300 | IPL | 2021-02-01 |  | Moon Pool |  | 0 | 0
29 | Wire rope package | WR 1051-01 | ACE | N/A | N/A | N/A | N/A | KOS | 2021-02-01 |  | Moon Pool | Included in item 24 footprint | 0 | 0
31 | ACE 110kW Zone 2 Closed Loop Diesel Hydraulic Power Unit DHPU | ACE2166 | ACE | 3000 | 1345 | 2308 | 4500 | KOS | 2021-02-01 |  | Moon Pool - Main Deck | No-weld, Bolt-up | 0 | 0
32 | ACE 110kW Zone 2 Closed Loop Diesel Hydraulic Power Unit Control Station | ACE2166CS | ACE | 500 | 400 | 1410 | 120 | KOS | 2021-02-01 |  | Moon Pool - Main Deck | No-weld, Bolt-up | 1 | 0
33 | ACE 144 Tonne WLL Hydraulic drum winch | ACE1694 | ACE | 2904 | 2404 | 2438 | 30000 | KOS | 2021-02-01 |  | Moon Pool - Main Deck | No-weld, Bolt-up | 0 | 0
34 | ACE 144 Tonne WLL Hydraulic drum winch, sliding base frame | ACE1714 | ACE | 4250 | 2708 | 390 | 6000 | KOS | 2021-02-01 |  | Moon Pool - Main Deck | No-weld, Bolt-up | 0 | 0
35 | Interconnecting Cable Set | UM564 | ACE | 1230 | 1230 | 430 | 300 | IPL | 2021-02-01 |  | Moon Pool |  | 0 | 0
36 | Water Cooling Hoses Set | N/A | ACE | 1230 | 1230 | 430 | 300 | IPL | 2021-02-01 |  | Moon Pool |  | 1 | 0
37 | Air start hose | N/A | ACE | 1230 | 1230 | 430 | 300 | IPL | 2021-02-01 |  | Moon Pool |  | 0 | 0
38 | Wire rope package | WR 1052-01 | ACE | N/A | N/A | N/A | N/A | KOS | 2021-02-01 |  | Moon Pool | Included in item 33 footprint | 0 | 0
40 | ACE 110kW Zone 2 Closed Loop Diesel Hydraulic Power Unit DHPU | ACE2167 | ACE | 3000 | 1345 | 2308 | 4500 | KOS | 2021-02-01 |  | Moon Pool - Main Deck | No-weld, Bolt-up | 0 | 1
41 | ACE 110kW Zone 2 Closed Loop Diesel Hydraulic Power Unit Control Station | ACE2167CS | ACE | 500 | 400 | 1410 | 120 | KOS | 2021-02-01 |  | Moon Pool - Main Deck | No-weld, Bolt-up | 0 | 0
42 | ACE 90 Tonnes SWL Horizontal | ACE3735 | ACE | 2200 | 1800 | 4700 | 3800 | KOS | 2021-02-01 |  | Moon Pool - Main Deck | No-weld, Bolt-up | 0 | 0
43 | ACE 90 Tonnes SWL Horizontal | ACE3767 | ACE | 2200 | 1800 | 4700 | 3800 | SHI | 2021-02-01 |  | Moon Pool - Main Deck | definite korea install | 0 | 0
44 | ACE 90 Tonnes SWL Horizontal | ACE3768 | ACE | 2200 | 1800 | 4700 | 3800 | KOS | 2021-02-01 |  | Moon Pool - Main Deck | No-weld, Bolt-up | 0 | 0
45 | ACE 120 Tonnes SWL Vertical | ACE1722 | ACE | 1225 | 1039 | 1753 | 2150 | KOS | 2021-02-01 |  | Moon Pool - Main Deck | No-weld, Bolt-up | 1 | 0
46 | ACE 120 Tonnes SWL Vertical | ACE1723 | ACE | 1225 | 1039 | 1753 | 2150 | KOS | 2021-02-01 |  | Moon Pool - Main Deck | No-weld, Bolt-up | 0 | 0
47 | ACE 120 Tonnes SWL Vertical | ACE1724 | ACE | 1225 | 1039 | 1753 | 2150 | KOS | 2021-02-01 |  | Moon Pool - Main Deck | No-weld, Bolt-up | 0 | 0
48 | ACE 120 Tonnes SWL Vertical | ACE3769 | ACE | 1225 | 1039 | 1753 | 2150 | IPL | 2021-02-01 |  | Moon Pool |  | 0 | 0
51 | ACE 550Te SWL Zone 2 Linear Winch Linear Winch (1) | ACE3641 | ACE | 13890 | 2875 | 1918 | 35000 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
52 | ACE 550Te SWL Zone 2 Linear Winch Linear Winch (2) | ACE3641 | ACE | 13890 | 2875 | 1918 | 35000 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
53 | ACE 420kW Safe Area Diesel Hydraulic Power Unit DHPU | ACE3648 | ACE | 9114 | 2420 | 2663 | 26000 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
54 | 16' Control Cabin | ACE 3657 | ACE | 4877 | 2438 | 2590 | 6395 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 1 | 0
55 | Interconnecting Hose Set (special) | UM678 | ACE | 1230 | 1230 | 430 | 300 | KOS | 2021-02-01 |  | South East Corner |  | 0 | 0
56 | Interconnecting Cable Set | IC3641 | ACE | 1230 | 1230 | 430 | 300 | KOS | 2021-02-01 |  | South East Corner |  | 0 | 1
57 | Wire rope package | WR 1049-01 | ACE | N/A | N/A | N/A | 30000 | KOS | 2021-02-01 |  | South East Corner | Included in item 58 footprint | 0 | 0
58 | South East Corner Wire rope storage drum | ACE3758 | ACE | 2750 | 3500 | 3500 | 30000 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
59 | Spare Wire rope package | WR 1050-01 | ACE | N/A | N/A | N/A | 30000 | KOS | 2021-02-01 |  | South East Corner | Included in item 59 footprint | 0 | 0
60 | South East Corner/North side Spare Wire rope storage drum | ACE3759 | ACE | 2750 | 3500 | 3500 | 30000 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 1
65 | ACE 125Te SWL Zone 2 Hydraulic Reel | ACE3667 | ACE | 2200 | 5000 | 3280 | 9500 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
66 | ACE Stand Alone Spooling Gear | ACE1768 | ACE | 4355 | 1160 | 385 | 1820 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 1 | 0
67 | ACE 75 Tonne WLL 3 Rollerbox | ACE2089 | ACE | 1800 | 870 | 1105 | 1850 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
68 | Interconnecting Hose Set | N/A | ACE | 1230 | 1230 | 439 | 300 | IPL | 2021-02-01 |  | South East Corner |  | 0 | 0
70 | ACE 60kW Open Loop Zone 2 Diesel Hydraulic Power Unit DHPU | ACE1656 | ACE | 2500 | 1330 | 2040 | 3500 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
71 | Water Cooling Hoses Set | N/A | ACE | 1230 | 1230 | 430 | 300 | IPL | 2021-02-01 |  | South East Corner |  | 0 | 0
72 | Air start hose | N/A | ACE | 1230 | 1230 | 430 | 300 | IPL | 2021-02-01 |  | South East Corner |  | 0 | 0
73 | ACE 300Te SWL Horizontal Sheave | ACE3733 | ACE | 2300 | 2305 | 880 | 7375 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 1 | 0
74 | ACE 300Te SWL Horizontal Sheave | ACE3734 | ACE | 2300 | 2305 | 880 | 7375 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
75 | ACE 300Te SWL Horizontal Sheave | ACE3841 | ACE | 2300 | 2305 | 880 | 7375 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
76 | ACE 350Te SWL Horizontal Sheave | ACE3732 | ACE | 4660 | 3390 | 3375 | 17365 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
77 | ACE 16' Tooling / Workshop Container Container | N/A | ACE | 4877 | 2438 | 2590 | 6395 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 1 | 0
78 | ACE 16' Spares Container Container | N/A | ACE | 4877 | 2438 | 2590 | 6395 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
84 | ACE 18Te WLL Safe Area Hydraulic Drum Winch | ACE1748 | ACE | 1570 | 1210 | 1460 | 4500 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
85 | ACE 45kW Safe Area Open Loop Diesel Hydraulic Power Unit DHPU | ACE3569 | ACE | 1980 | 1056 | 1900 | 3500 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
86 | Interconnecting Cable Set | UM664 | ACE | 1230 | 1230 | 430 | 300 | KOS | 2021-02-01 |  | South East Corner |  | 0 | 0
87 | Water Cooling Hoses Set | N/A | ACE | 1230 | 1230 | 430 | 300 | IPL | 2021-02-01 |  | South East Corner |  | 0 | 0
88 | Air start hose | N/A | ACE | 1230 | 1230 | 430 | 300 | IPL | 2021-02-01 |  | South East Corner |  | 1 | 0
89 | ACE 18Te WLL Safe Area Hydraulic Drum Winch | ACE1749 | ACE | 1570 | 1210 | 1460 | 4500 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
90 | ACE 45kW Safe Area Open Loop Diesel Hydraulic Power Unit DHPU | ACE3570 | ACE | 1980 | 1056 | 1900 | 3500 | KOS | 2021-02-01 |  | South East Corner | No-weld, Bolt-up | 0 | 0
91 | Interconnecting Cable Set | UM557 | ACE | 1230 | 1230 | 430 | 300 | KOS | 2021-02-01 |  | South East Corner |  | 0 | 0
92 | Water Cooling Hoses Set | N/A | ACE | 1230 | 1230 | 430 | 300 | IPL | 2021-02-01 |  | South East Corner |  | 0 | 0
93 | Air start hose | N/A | ACE | 1230 | 1230 | 430 | 300 | IPL | 2021-02-01 |  | South East Corner |  | 0 | 0
102 | ACE 90Te SWL Subsea snatchblock | ACE3736 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 0
103 | ACE 90Te SWL Subsea snatchblock | ACE3737 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 0
104 | ACE 90Te SWL Subsea snatchblock | ACE3738 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 0
105 | ACE 90Te SWL Subsea snatchblock | ACE3739 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 0
106 | ACE 90Te SWL Subsea snatchblock | ACE3740 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 1
107 | ACE 90Te SWL Subsea snatchblock | ACE3741 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 1 | 0
108 | ACE 90Te SWL Subsea snatchblock | ACE3742 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 0
109 | ACE 90Te SWL Subsea snatchblock | ACE3743 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 0
110 | ACE 90Te SWL Subsea snatchblock | ACE3744 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 0
111 | ACE 90Te SWL Subsea snatchblock | ACE3745 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 1 | 0
112 | ACE 90Te SWL Subsea snatchblock | ACE3746 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 1
113 | ACE 90Te SWL Subsea snatchblock | ACE3747 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 0
114 | ACE 90Te SWL Subsea snatchblock | ACE3748 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 0
115 | ACE 90Te SWL Subsea snatchblock | ACE3749 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 0
116 | ACE 90Te SWL Subsea snatchblock | ACE3750 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 0
117 | ACE 90Te SWL Subsea snatchblock | ACE3751 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 1 | 0
118 | ACE 90Te SWL Subsea snatchblock | ACE3752 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 0
119 | ACE 90Te SWL Subsea snatchblock | ACE3753 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 0
120 | ACE 90Te SWL Subsea snatchblock | ACE3754 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 1
121 | ACE 90Te SWL Subsea snatchblock | ACE3755 | ACE | 1326 | 667 | 2605 | 1250 | SHI | 2021-02-01 |  | Pontoon | definite korea install | 0 | 0
94 | ACE 75Te SWL Swivel head Fairlead | AC1917 | ACE | 1325 | 1000 | 2530 | 3200 | SHI | Done |  | Moon pool cellar deck | Install complete | 1 | 0
95 | ACE 75Te SWL Swivel head Fairlead | AC1918 | ACE | 1325 | 1000 | 2530 | 3200 | SHI | Done |  | Moon pool cellar deck | Install complete | 0 | 0
96 | ACE 75Te SWL Swivel head Fairlead | AC1919 | ACE | 1325 | 1000 | 2530 | 3200 | SHI | Done |  | Moon pool cellar deck | Install complete | 0 | 1
97 | ACE 75Te SWL Swivel head Fairlead | AC1920 | ACE | 1325 | 1000 | 2530 | 3200 | SHI | Done |  | Moon pool cellar deck | Install complete | 0 | 0
98 | ACE 75Te SWL Swivel head Fairlead - Grillage | AC1917BF | ACE | TBC | TBC | TBC | 1300 | SHI | Done |  | Moon pool cellar deck | Install complete | 0 | 0
99 | ACE 75Te SWL Swivel head Fairlead - Grillage | AC1918BF | ACE | TBC | TBC | TBC | 1300 | SHI | Done |  | Moon pool cellar deck | Install complete | 1 | 1
100 | ACE 75Te SWL Swivel head Fairlead - Grillage | AC1919BF | ACE | TBC | TBC | TBC | 1300 | SHI | Done |  | Moon pool cellar deck | Install complete | 0 | 0
101 | ACE 75Te SWL Swivel head Fairlead - Grillage | AC1920BF | ACE | TBC | TBC | TBC | 1300 | SHI | Done |  | Moon pool cellar deck | Install complete | 0 | 0
128 | 10' x 8' Rigging Loft | TBC | Worley |  |  |  | 3000 | IPL | see comment |  | TBA | Just prior to sailaway | 0 | 0
129 | 20' x 8' Tool & Equipment store | TBC | Worley |  |  |  | 5000 | IPL | see comment |  | TBA | Just prior to sailaway | 1 | 0
130 | 20' x 8' Project Materials store | TBC | Worley |  |  |  | 5000 | IPL | see comment |  | TBA | Just prior to sailaway | 0 | 0
122 | Temporary Sea Water Booster Pump (Diesel Engine Driven) | TBC | Worley | 3352 | 2133 | 1524 | 5000 | IPL | TBC |  | Cellar Deck |  | 0 | 0
123 | Temporary Sea Water Booster Pump (Diesel Engine Driven) | TBC | Worley | 3352 | 2133 | 1524 | 5000 | IPL | TBC |  | Cellar Deck |  | 0 | 0
124 | Temp Sea Water Filter (For Temp Sea Water Booster Pump) | TBC | Worley | 2133 | 1828 | 2133 | 1090 | IPL | TBC |  | Cellar Deck | Operational weight is 2190Kg | 1 | 0
125 | Temp Sea Water Filter (For Temp Sea Water Booster Pump) | TBC | Worley | 2133 | 1828 | 2133 | 1090 | IPL | TBC |  | Cellar Deck | Operational weight is 2190Kg | 0 | 1
126 | Back Up Temp Air Compressor (Diesel Engine driven) | TBC | Worley | 5791 | 2133 | 2438 | 9400 | IPL | TBC |  | Cellar Deck |  | 0 | 0
127 | Diesel Tank | TBC | Worley | 2438 | 2438 | 1524 | 1680 | IPL | TBC |  | Cellar Deck | Weight when full is 6180Kg | 0 | 0
131 | Shut down Valve | TBC | Well Test | 1219 | 609 | 1371 | 906 | [5 empty] | 0 | 0
132 | Water Surge Tank | TBC | Well Test | 2895 | 2438 | 6096 | 14632 |  |  |  |  | Wet weight 35,941 Kg | 0 | 0
133 | 50 BBL Marine portable tank | TBC | Well Test | 2997 | 2438 | 2590 | 4077 |  |  |  |  | Wet weight 14,732 Kg | 0 | 0
134 | 50 BBL Marine portable tank | TBC | Well Test | 2997 | 2438 | 2590 | 4077 |  |  |  |  | Wet weight 14,732 Kg | 0 | 0
135 | 50 BBL Marine portable tank | TBC | Well Test | 2997 | 2438 | 2590 | 4077 |  |  |  |  | Wet weight 14,732 Kg | 0 | 0
136 | 50 BBL Marine portable tank | TBC | Well Test | 2997 | 2438 | 2590 | 4077 |  |  |  |  | Wet weight 14,732 Kg | 1 | 0
137 | ESD Panel | TBC | Well Test | 1168 | 1016 | 1905 | 1133 | [5 empty] | 0 | 0
138 | Spill Kit | TBC | Well Test | 1828 | 914 | 914 | 906 | [5 empty] | 0 | 0
139 | Tool Box | TBC | Well Test | 2133 | 1524 | 1955 | 2265 | [5 empty] | 0 | 1
140 | Pressure Test Pump | TBC | Well Test | 1676 | 660 | 1397 | 589 | [5 empty] | 1 | 0
141 | Pump Skid | TBC | Water Filtration | 1828 | 1219 | 1219 | 2478 | [5 empty] | 0 | 0
142 | Pump Skid | TBC | Water Filtration | 1828 | 1219 | 1219 | 2478 | [5 empty] | 0 | 0
143 | Gas Floatation Unit | TBC | Water Filtration | 6096 | 2590 | 3200 | 2478 |  |  |  |  | Wet weight 32,861 Kg | 1 | 0
144 | Cartridge Filter Skid | TBC | Well Clean | 2133 | 1219 | 2133 | 1586 |  |  |  |  | Wet weight 1,798 Kg | 0 | 0
145 | Manifold | TBC | Well Clean | 1828 | 1219 | 1219 | 1359 |  |  |  |  | Wet weight 1,576 Kg | 0 | 0
146 | Carbon Vessel Skid | TBC | Well Clean | 3048 | 1524 | 2743 | 4711 |  |  |  |  | Wet weight 8,973 Kg | 0 | 0
147 | Carbon Vessel Skid | TBC | Well Clean | 3048 | 1524 | 2743 | 4711 |  |  |  |  | Wet weight 8,973 Kg | 0 | 0
148 | Diaphragm Pump | TBC | Well Clean | 914 | 914 | 1219 | 680 |  |  |  |  | Wet weight 786 Kg | 0 | 0
149 | Diaphragm Pump | TBC | Well Clean | 914 | 914 | 1219 | 680 |  |  |  |  | Wet weight 786 Kg | 0 | 0
150 | Tool Box | TBC | Well Clean | 1828 | 914 | 914 | 2265 | [5 empty] | 1 | 0
[13 empty] | 0 | 0