## Sheet1
Item No | Discription of Item to be loaded | Item ID | Owner of Item | Length (mm) | Width (mm) | Height (mm) | Weight (Kg) | Load location | Projected load Date | Projected off load Date | Where item is to be located | Comments | Hazards | Risk
21 | Reel stand and Spooling gear Grillage | ACE3761 | ACE | 4885 | 3856 | 327 | 4659 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 1 | 0
22 | Reel stand and Spooling gear Grillage | ACE3762 | ACE | 4885 | 3138 | 327 | 4432 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 0 | 0
23 | Reel stand and Spooling gear Grillage | ACE3763 | ACE | 729 | 70 | 1200 | 350 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 0 | 0
30 | West Moon Pool steering winch grillage | ACE3764 | ACE | 14222 | 2506 | 377 | 7861 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 1 | 1
39 | East Moon Pool steering winch grillage | ACE3766 | ACE | 14222 | 2506 | 377 | 7861 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 0 | 1
49 | ACE 110kW Diesel Hydraulic Power Unit DHPU - West grillage | ACE 2166BF | ACE | 729 | 327 | 327 | 350 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 0 | 0
50 | ACE 110kW Diesel Hydraulic Power Unit DHPU - East grillage | ACE 2166BK | ACE | 327 | 327 | 327 | 350 | 3 | 2020-07-01 |  | South East Corner | definite korea install | 0 | 0
61 | ACE 550Te SWL Linear Winch South East Corner Grillage (1) | ACE3727 | ACE | 8200 | 3500 | 1885 | 7495 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 0 | 0
62 | ACE 550Te SWL Linear Winch South East Corner Grillage (2) | ACE3728 | ACE | 8200 | 3500 | 635 | 7020 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 0 | 0
63 | ACE 550Te SWL Linear Winch South East Corner Grillage (3) | ACE3729 | ACE | 4924 | 2876 | 2206 | 11394 | SHI | 2020-07-01 |  | South East Corner | definite korea install | 0 | 1
64 | ACE 550Te SWL Linear Winch South East Corner Grillage (3) | ACE3730 | ACE | 4924 | 2876 | 2389 | 12643 | SHI | 2020-07-01 |  | Moon Pool | definite korea install | 1 | 0
69 | South East Corner reel stand / spooling gear grillage | ACE3765 | ACE | 4653 | 3750 | 876 | 3710 | SHI | 2020-07-01 |  | Moon Pool | definite korea install | 0 | 1
79 | East pull in Grillage (1) | ACE3767 | ACE | 8240 | 4260 | 2540 | 16168 | SHI | 2020-07-01 |  | Moon Pool | definite korea install | 0 | 0
80 | East pull in Grillage (2) | ACE3768 | ACE | 12000 | 3500 | 921 | 13327 | SHI | 2020-07-01 |  | Moon Pool | definite korea install | 0 | 0
81 | East pull in Grillage (3) | ACE3769 | ACE | 12000 | 3500 | 921 | 13327 | SHI | 2020-07-01 |  | Moon Pool | definite korea install | 0 | 0
82 | East pull in Grillage (4) | ACE3770 | ACE | 6996 | 3500 | 921 | 11573 | SHI | 2020-07-01 |  | Moon Pool | definite korea install | 0 | 0
83 | South pull in Grillage | ACE3771 | ACE | 14863 | 4217 | 1611 | 20500 | SHI | 2020-07-01 |  | Moon Pool | definite korea install | 1 | 0
1 | 550 Te SWL Zone 2 linear winch | ACE3640 | ACE | 8620 | 2885 | 1635 | 46000 | SHI | 2021-02-01 |  | Moon Pool | Likely install in Korea, GoM Contingency | 0 | 0
2 | ACE 220kW Zone 2 Diesel Hydraulic Power Unit | ACE 470 | ACE | 6170 | 2540 | 2790 | 15000 | KOS | 2021-02-01 |  | Moon Pool | No-weld, Bolt-up | 0 | 0
3 | ACE 550Te SWL Linear Winch Hang off | ACE3726 | ACE | 4814 | 1410 | 2959 | 10948 | SHI | 2021-02-01 |  | Moon Pool | Likely install in Korea, GoM Contingency | 0 | 0
4 | ACE 550Te SWL Linear Winch Hang off
5 | ACE 550te Trunnion Arrangement
New | Control Cabin Steel Beams for Seafastening (x2)
6 | 16' Control Cabin
7 | Interconnecting Hose Set (special)
8 | Interconnecting Hose Set (special)
9 | Interconnecting Cable Set
10 | Water Cooling Hoses Set
11 | Air start hose
12 | Wire rope package
13 | Northside wire rope storeage drum
14 | ACE 125Te SWL Zone 2 Hydraulic Reel
15 | ACE Stand Alone Spooling Gear
16 | ACE 75 Tonne WLL 3 Rollerbox
17 | ACE 60kW Open Loop Zone 2 Diesel
18 | Interconnecting Cable Set
19 | Water Cooling Hoses Set
20 | Air start hose
24 | ACE 144 Tonne WLL Hydraulic drum winch
25 | ACE 144 Tonne WLL Hydraulic drum winch, sliding base frame
26 | Interconnecting Cable Set
27 | Water Cooling Hoses Set
28 | Air start hose
29 | Wire rope package
31 | ACE 110kW Zone 2 Closed Loop Diesel Hydraulic Power Unit DHPU
32 | ACE 110kW Zone 2 Closed Loop Diesel Hydraulic Power Unit Control Station
33 | ACE 144 Tonne WLL Hydraulic drum winch
34 | ACE 144 Tonne WLL Hydraulic drum winch, sliding base frame
35 | Interconnecting Cable Set
36 | Water Cooling Hoses Set
37 | Air start hose
38 | Wire rope package
40 | ACE 110kW Zone 2 Closed Loop Diesel Hydraulic Power Unit DHPU
41 | ACE 110kW Zone 2 Closed Loop Diesel Hydraulic Power Unit Control Station
42 | ACE 90 Tonnes SWL Horizontal
43 | ACE 90 Tonnes SWL Horizontal
44 | ACE 90 Tonnes SWL Horizontal
45 | ACE 120 Tonnes SWL Vertical
46 | ACE 120 Tonnes SWL Vertical
47 | ACE 120 Tonnes SWL Vertical
48 | ACE 120 Tonnes SWL Vertical
51 | ACE 550Te SWL Zone 2 Linear Winch Linear Winch (1)
52 | ACE 550Te SWL Zone 2 Linear Winch Linear Winch (2)
53 | ACE 420kW Safe Area Diesel Hydraulic Power Unit DHPU
54 | 16' Control Cabin
55 | Interconnecting Hose Set (special)
56 | Interconnecting Cable Set
57 | Wire rope package
58 | South East Corner Wire rope storage drum
59 | Spare Wire rope package
60 | South East Corner/North side Spare Wire rope storage drum
65 | ACE 125Te SWL Zone 2 Hydraulic Reel
66 | ACE Stand Alone Spooling Gear
67 | ACE 75 Tonne WLL 3 Rollerbox
68 | Interconnecting Hose Set
70 | ACE 60kW Open Loop Zone 2 Diesel Hydraulic Power Unit DHPU
71 | Water Cooling Hoses Set
72 | Air start hose
73 | ACE 300Te SWL Horizontal Sheave
74 | ACE 300Te SWL Horizontal Sheave
75 | ACE 300Te SWL Horizontal Sheave
76 | ACE 350Te SWL Horizontal Sheave
77 | ACE 16' Tooling / Workshop Container Container
78 | ACE 16' Spares Container Container
84 | ACE 18Te WLL Safe Area Hydraulic Drum Winch
85 | ACE 45kW Safe Area Open Loop Diesel Hydraulic Power Unit DHPU
86 | Interconnecting Cable Set
87 | Water Cooling Hoses Set
88 | Air start hose
89 | ACE 18Te WLL Safe Area Hydraulic Drum Winch
90 | ACE 45kW Safe Area Open Loop Diesel Hydraulic Power Unit DHPU
91 | Interconnecting Cable Set
92 | Water Cooling Hoses Set
93 | Air start hose
102 | ACE 90Te SWL Subsea snatchblock
103 | ACE 90Te SWL Subsea snatchblock
104 | ACE 90Te SWL Subsea snatchblock
105 | ACE 90Te SWL Subsea snatchblock
106 | ACE 90Te SWL Subsea snatchblock
107 | ACE 90Te SWL Subsea snatchblock
108 | ACE 90Te SWL Subsea snatchblock
109 | ACE 90Te SWL Subsea snatchblock
110 | ACE 90Te SWL Subsea snatchblock
111 | ACE 90Te SWL Subsea snatchblock
112 | ACE 90Te SWL Subsea snatchblock
113 | ACE 90Te SWL Subsea snatchblock
114 | ACE 90Te SWL Subsea snatchblock
115 | ACE 90Te SWL Subsea snatchblock
116 | ACE 90Te SWL Subsea snatchblock
117 | ACE 90Te SWL Subsea snatchblock
118 | ACE 90Te SWL Subsea snatchblock
119 | ACE 90Te SWL Subsea snatchblock
120 | ACE 90Te SWL Subsea snatchblock
121 | ACE 90Te SWL Subsea snatchblock
94 | ACE 75Te SWL Swivel head Fairlead
95 | ACE 75Te SWL Swivel head Fairlead
96 | ACE 75Te SWL Swivel head Fairlead
97 | ACE 75Te SWL Swivel head Fairlead
98 | ACE 75Te SWL Swivel head Fairlead - Grillage
99 | ACE 75Te SWL Swivel head Fairlead - Grillage
100 | ACE 75Te SWL Swivel head Fairlead - Grillage
101 | ACE 75Te SWL Swivel head Fairlead - Grillage
128 | 10' x 8' Rigging Loft
129 | 20' x 8' Tool & Equipment store
130 | 20' x 8' Project Materials store
122 | Temporary Sea Water Booster Pump (Diesel Engine Driven)
123 | Temporary Sea Water Booster Pump (Diesel Engine Driven)
124 | Temp Sea Water Filter (For Temp Sea Water Booster Pump)
125 | Temp Sea Water Filter (For Temp Sea Water Booster Pump)
126 | Back Up Temp Air Compressor (Diesel Engine driven)
127 | Diesel Tank
131 | Shut down Valve
132 | Water Surge Tank
133 | 50 BBL Marine portable tank
134 | 50 BBL Marine portable tank
135 | 50 BBL Marine portable tank
136 | 50 BBL Marine portable tank
137 | ESD Panel
138 | Spill Kit
139 | Tool Box
140 | Pressure Test Pump
141 | Pump Skid
142 | Pump Skid
143 | Gas Floatation Unit
144 | Cartridge Filter Skid
145 | Manifold
146 | Carbon Vessel Skid
147 | Carbon Vessel Skid
148 | Diaphragm Pump
149 | Diaphragm Pump
150 | Tool Box